## Slide 2
MEAN MARKETPLACE AGILE SUMMARY
McLean, VA
March 11, 2015

## Slide 3: Team mean roles and responsibilities
Vinay Katari – Team Lead/Product Owner/Scrum Master
Taran Dhupar – Frontend Developer/DevOps
Mehul Soni – Backend Developer
Allen Stone – UX/UI Team
Christine Cade – UX/UI Team

## Slide 4: Sprint 0 – Initial/vision setting
Date: Tuesday March 10, 2015
Time: 6:00 – 7:00 PM
Cadence: 1 Hour
# of Standups: 0
Overall Thoughts & Lessons Learned:
We executed our initial sprint very well. We started out rough but got things going pretty quickly. Need to ensure that we are doing standups on time.

## Slide 5: Sprint 1
Date: Tuesday March 10, 2015
Time: 7:00 – 9:00 PM
Cadence: 2 Hour
# of Standups: 2
Sprint Planning: 15 min
Retrospective: 5 min
# of Tasks: 11/12
Velocity: 18
Overall Thoughts: We finished the sprint and were able to deliver all of our expected deliverables: SDD (architecture diagram, UI artifacts, db schema, technology stack), Product backlog, UI artifacts

## Slide 6: Sprint 2
Date: Wednesday March 11, 2015
Time: 5:30 – 7:30 PM
Cadence: 2 Hour
# of Standups: 3
Sprint Planning: 15 min
Retrospective: 0 min
# of Tasks Finish: 1/5 – 4 Items Moved to Sprint 3
Velocity: 2/10 – 8 Points Moved to Sprint 3
Overall Thoughts: This sprint did not go as well, we ended up under estimating the work items and as such had to move items to the next sprint. This poor estimation was noted in the retrospective.

## Slide 7: Sprint 3
Date: Wednesday March 11, 2015
Time: 7:30 – 9:20 PM
Cadence: 2 Hour
# of Standups: 4
Sprint Planning: 5 min
Retrospective: 5 min
# of Tasks Finish: 6/7 Tasks
Velocity: did not calculate
Overall Thoughts: Process was the first thing that started to break but mostly due to the fact that we were unable to finish things. We ran into issues and as such ceremonies broke. Fix – Increase timebox to 4 hrs.

## Slide 8: Sprint 4
Date: Thursday March 12, 2015
Time: 5:00 – 9:00 PM
Cadence: 4 Hour
# of Standups: 6
Sprint Planning: 15 min
Retrospective: min
# of Tasks Finish: 19/21 Tasks
Velocity: did not calculate
Overall Thoughts: Increased time box allowed us to work more efficiently without being disturbed. We did however continue to do standups. Additionally, moved away from JIRA and used whiteboards to facilitate.